## Sheet1
ID | Module | Test Case | Input | Expected Output | Actual Output | Result
AUTH-001 | Authentication | UI | Launch App to Login | Email, Password, Login button visible | Loaded perfectly | Pass
AUTH-002 | Authentication | UI | Check logo and header | Logo is centered, text must be centered | Logo is centered, text is centered | Pass
AUTH-003 | Authentication | UX | Tap Email field | Keyboard opens with @ symbol | Keyboard opens with @ symbol | Pass
AUTH-004 | Authentication | UX | Tap Password field | Alphanumeric keyboard opens | Keyboard opened correctly. | Pass
AUTH-005 | Authentication | UI | Type in password field | Characters are hidden as bullets | Text masked immediately. | Pass
AUTH-006 | Authentication | Functionality | Click 'eye' icon | Password unmasks | Unmasked successfully. | Pass
AUTH-007 | Authentication | Functionality | Click 'eye' icon again | Password masks | Masked successfully. | Pass
AUTH-008 | Authentication | Validation | Submit empty form | Error: 'Please enter both email and password' | Toast message appeared correctly. | Pass
AUTH-009 | Authentication | Validation | Email: 'admin', Pass: '1234' | Error: 'Invalid email or password' | Toast message appeared correctly. | Pass
AUTH-010 | Authentication | Validation | Email: 'test@uniflow', Pass: 'pass' | Error: 'Invalid email or password' | Toast message appeared correctly. | Pass
AUTH-011 | Authentication | Validation | Email: '@uniflow.com', Pass: 'pass' | Error: 'Invalid email or password' | Toast message appeared correctly. | Pass
AUTH-012 | Authentication | Functionality | Valid Email, Empty Pass | Error: 'Please enter both email and password' | Toast message appeared correctly. | Pass
AUTH-013 | Authentication | Validation | Email: 'user@uniflow.com ', Pass: 'test' | Trailing space trimmed automatically | Trimming worked, login proceeded. | Pass
AUTH-014 | Authentication | Validation | Email: ' user@uniflow.com', Pass: 'test' | Leading space trimmed automatically | Trimming worked. | Pass
AUTH-015 | Authentication | Logic | Unregistered Email | Error: 'Invalid email or password' | Toast message appeared correctly. | Pass
AUTH-016 | Authentication | Logic | Correct Email, Wrong Pass | Error: 'Invalid email or password' | Toast message appeared correctly. | Pass
AUTH-017 | Authentication | Security | Email: 'student@uniflow.in', Pass: 'OR 1=1' | SQLi blocked, login fails | Sanitized. Did not crash. | Pass
AUTH-018 | Authentication | Security | Email: '<script>alert(1)</script>' | XSS blocked, invalid format | Failed validation early. | Pass
AUTH-019 | Authentication | Positive | Valid student credentials | Login succeeds, navigates to Dashboard | Logged in successfully. | Pass
AUTH-022 | Authentication | Logic | Spam click Login button 10 times | Only 1 API call sent | Button disabled itself on first click. | Pass
AUTH-023 | Authentication | UI | Check loading state | Spinner appears on button click | Small circular spinner replaced button text. | Pass
AUTH-024 | Authentication | Logic | Case insensitivity on Email | Type 'STUDENT@iiitn.ac.in' | Toast message appeared correctly. | Pass
AUTH-025 | Authentication | Logic | Case sensitivity on Password | Type wrong case for password | Toast message appeared correctly. | Pass
AUTH-026 | Authentication | Session | Login, press OS Home, reopen app | Still on Dashboard | Session maintained perfectly. | Pass
AUTH-027 | Authentication | Session | Login, swipe kill app, reopen | Auto-route to Dashboard | Bypassed login screen via saved token. | Pass
AUTH-028 | Authentication | Session | Press hardware back button from Dashboard | App minimizes, does not return to login | App closed as expected. | Pass
AUTH-029 | Authentication | Navigation | Click 'Forgot Password' | Opens Password Reset screen | Nothing yet | Fail
AUTH-030 | Authentication | Navigation | Click 'Sign Up' | Opens Registration screen | Navigated properly. | Pass
AUTH-031 | Authentication | UX | Press 'Done' on keyboard while in Password | Triggers login submission | Keyboard dismissed but didn't submit form. | Fail
AUTH-032 | Authentication | Logic | Paste email into field | Pasted text is accepted | Text pasted and validated. | Pass
AUTH-033 | Authentication | Security | Paste password into field | Pasted text is masked | Text pasted and masked instantly. | Pass
AUTH-034 | Authentication | Security | Copy from password field | OS prevents copying | Could not select text to copy. | Pass
AUTH-035 | Authentication | UX | Screen rotation during typing | Text stays in fields | Activity restarted, text wiped out. | Fail
AUTH-036 | Authentication | Logic | Email length > 100 chars | Handled gracefully | Input truncated at 50 chars. | Pass
AUTH-037 | Authentication | Performance | Login on 3G throttle | Handles slow network gracefully | Spinner spun for 15s then timed out cleanly. | Pass
AUTH-038 | Authentication | Logic | Lockout policy (if applicable) | 5 wrong attempts locks account | Account locked for 5 minutes. | Pass
AUTH-039 | Authentication | Logic | Login with disabled account | Error: 'Account deactivated' | Showed 'Contact Administrator'. | Pass
AUTH-040 | Authentication | Logic | Login with unverified email | Error: 'Please verify email' | Logged in anyway. Verification bypass bug. | Fail
AUTH-041 | Authentication | UX | Keyboard blocks Login button | UI scrolls up to keep button visible | Button was hidden behind keyboard on 5-inch device. | Fail
AUTH-042 | Authentication | UI | Dark Mode toggle | Screen colors invert, text readable | Text in email field became white on white background. | Fail
AUTH-043 | Authentication | UX | Change OS font size to Huge | UI scales without overlapping | Layout broke, 'Forgot Password' pushed off screen. | Fail
AUTH-044 | Authentication | Security | Clear App Data in Android settings | Removes stored tokens | Opened app, asked to login again. | Pass
AUTH-045 | Authentication | Security | Check logs via Android Studio | Passwords should not be printed | Logcat showed password in plaintext during API call. | Fail
AUTH-046 | Authentication | Logic | Concurrent logins | Login on Phone A, then Phone B | Phone A was forced out when Phone B logged in. | Pass
AUTH-047 | Authentication | Network | Drop network exactly during API response | Graceful error handling | App threw JSON parsing error on screen. | Fail
AUTH-048 | Authentication | Logic | Email with subdomain (student@cs.uniflow.in) | Accepted valid format | Accepted correctly. | Pass
AUTH-049 | Authentication | Logic | Email with plus addressing (test+1@uniflow.in) | Accepted valid format | Accepted correctly. | Pass
AUTH-051 | Authentication | UI | Error message clears on typing | Red text disappears when user edits field | Error text stayed until next submit click. | Fail
AUTH-052 | Authentication | Logic | Password > 50 characters | Does not crash | Accepted and processed safely. | Pass
AUTH-053 | Authentication | Logic | Special characters in password | Accepts valid specials (@, #, etc.) | Logged in successfully. | Pass
AUTH-054 | Authentication | Validation | Non-ASCII chars in email | Error: Invalid format | Caught invalid characters (e.g., emojis). | Pass
AUTH-063 | Authentication | Validation | Trailing space in password | Rejects (do not trim passwords) | Rejected 'Valid123 ' as wrong password. Good. | Pass
AUTH-064 | Authentication | Validation | Leading space in password | Rejects | Rejected correctly. | Pass
AUTH-065 | Authentication | UI | Check field focus on load | Email field auto-focused | No field was auto-focused. | Fail
AUTH-067 | Authentication | UX | TalkBack/Accessibility | Fields read aloud correctly | TalkBack read 'Edit box, Email'. | Pass
AUTH-068 | Authentication | Logic | SQL wildcard in Email: '%' | Sanitized | Treated as string, threw format error. | Pass
AUTH-069 | Authentication | Network | DNS failure simulation | Shows 'Network Error' | Showed generic connection error. | Pass
AUTH-070 | Authentication | UI | Click outside keyboard | Keyboard dismisses | Keyboard closed on tap outside. | Pass
AUTH-071 | Authentication | State | App paused by phone call during login | Resumes correctly | Resumed with form intact. | Pass
AUTH-072 | Authentication | Logic | Submit via hardware Enter key (Bluetooth keyboard) | Form submits | Submitted correctly. | Pass
AUTH-075 | Authentication | End-to-End | Complete happy path login | Works flawlessly under 2s | Completed in 1.1s. | Pass
REG-001 | Registration | UI | Navigate to Sign Up screen | Fields: Name, Email, Pass, Confirm Pass, Submit | All 4 fields and button visible. | Pass
REG-002 | Registration | UX | Check Placeholders | Read 'Full Name', 'College Email', etc. | Placeholders are clear. | Pass
REG-003 | Registration | Validation | Submit entirely blank form | Errors on all 4 fields | 4 toast messages stacked. Looks messy. | Fail
REG-004 | Registration | Validation | Name < 2 characters | Error: 'Name too short' | Error showed inline. | Pass
REG-005 | Registration | Validation | Name with numbers (John123) | Error: 'Name must be alphabetic' | Accepted numbers in name. Bug. | Fail
REG-006 | Registration | Validation | Name with specials (John@Doe) | Error: 'Invalid characters in name' | Accepted special characters. Bug. | Fail
REG-007 | Registration | Validation | Name with spaces/hyphens (Mary Jane-Watson) | Accepted | Accepted correctly. | Pass
REG-008 | Registration | Validation | Email: invalid domain | Error: 'Use college domain' (if restricted) | Allowed gmail.com instead of uniflow.edu.in. | Fail
REG-009 | Registration | Logic | Email: Already exists in DB | Error: 'Email already registered' | Showed 'Email taken' message. | Pass
REG-010 | Registration | Logic | Email: Upper case handling | Converted to lower case on submit | Checked DB, saved as lowercase. | Pass
REG-011 | Registration | Validation | Password < 8 chars | Error: 'Min 8 characters' | Showed error correctly. | Pass
REG-012 | Registration | Validation | Password lacks uppercase | Error: 'Needs uppercase letter' | Accepted all lowercase password. Security risk. | Fail
REG-013 | Registration | Validation | Password lacks number | Error: 'Needs 1 number' | Showed error correctly. | Pass
REG-014 | Registration | Validation | Password lacks special char | Error: 'Needs special character' | Showed error correctly. | Pass
REG-015 | Registration | Logic | Confirm Password matches | Pass validation | Validation passed. | Pass
REG-016 | Registration | Logic | Confirm Password mismatch | Error: 'Passwords do not match' | Error showed as soon as focus left field. | Pass
REG-017 | Registration | Security | Paste into Confirm Password | Disabled/Blocked | Was able to paste. Defeats purpose of field. | Fail
REG-018 | Registration | Functionality | Click 'eye' on Pass and Confirm Pass | Toggles visibility for both | Worked for both independently. | Pass
REG-019 | Registration | UI | Submit valid form | Spinner appears, button disables | Button disabled, prevented double click. | Pass
REG-020 | Registration | Positive | Valid student registration | Shows success, routes to Login | Routed to Login with success Toast. | Pass
REG-021 | Registration | Integration | Check DB for new user | User row exists, password hashed | Found in DB, password is bcrypt hashed. | Pass
REG-022 | Registration | State | Rotate screen during input | Inputs remain | Inputs cleared on rotation. | Fail
REG-023 | Registration | Navigation | Click 'Already have an account? Login' | Navigates back to Login | Navigated properly. | Pass
REG-024 | Registration | Network | Turn off WiFi mid-submit | Error: 'Network error' | Crashed with SocketTimeoutException. | Fail
REG-025 | Registration | Logic | Name length > 50 chars | Truncates or errors gracefully | UI pushed out of bounds, text cut off. | Fail
REG-026 | Registration | Logic | Email length > 100 chars | Errors gracefully | Threw 500 error from backend (DB limit hit). | Fail
REG-027 | Registration | Security | SQL Injection in Name: ' OR 1=1; DROP TABLE users; -- | Sanitized | Stored exactly as typed, did not execute. | Pass
REG-028 | Registration | Security | XSS in Name: <script>alert(1)</script> | Sanitized | Stored as text. | Pass
REG-029 | Registration | UX | Tab order via hardware keyboard | Name -> Email -> Pass -> Confirm | Order was Name -> Pass -> Email. Messed up. | Fail
REG-030 | Registration | UI | Keyboard pushes UI up | All fields remain visible | Confirm Password hidden behind keyboard. | Fail
REG-031 | Registration | UX | Error messages disappear on edit | Red text clears | Cleared when typing started. | Pass
REG-032 | Registration | Logic | Concurrent registration same email | Two phones submit same email at exact same time | DB locked one, returned 'Already exists' to other. | Pass
REG-033 | Registration | Logic | Terms & Conditions checkbox | Must be checked to submit | No checkbox exists on UI. Requirements missed? | Fail
REG-035 | Registration | Security | Check payload via proxy | Sent over HTTPS, not plaintext HTTP | Verified SSL. | Pass
REG-036 | Registration | Logic | Email with trailing space | Trims and validates | Trimmed automatically. | Pass
REG-037 | Registration | Logic | Password with spaces | Error: 'Spaces not allowed' | Accepted password with spaces. | Fail
REG-038 | Registration | UI | Dark Mode readability | Labels readable | Labels are dark gray on black bg. Unreadable. | Fail
REG-039 | Registration | UI | Large Font size OS setting | Layout doesn't break | Layout shifted, button overlaps text. | Fail
REG-040 | Registration | Functionality | Auto-login post registration | Routes straight to Dashboard (if required) | Forced manual login instead. Check spec. | Fail
REG-041 | Registration | Network | Submit on slow 3G | Handles timeout | Threw 'Request timed out' after 30s. | Pass
REG-042 | Registration | Logic | Send OTP to email (if applicable) | OTP received | Email received in 5 seconds. | Pass
REG-043 | Registration | Logic | Enter invalid OTP | Error: 'Invalid code' | Showed error. | Pass
REG-044 | Registration | Logic | Enter valid OTP | Account verified | Verified and routed to Login. | Pass
REG-045 | Registration | Logic | Resend OTP | New email arrives | Arrived successfully. | Pass
REG-046 | Registration | Logic | OTP cooldown timer | Cannot spam resend | Resend button disabled with 60s countdown. | Pass
REG-047 | Registration | Logic | Register with admin email format | Blocked if reserved | Allowed me to register 'admin@uniflow.in'. | Fail
REG-048 | Registration | Logic | HTML tags in Email | Error: 'Invalid format' | Rejected correctly. | Pass
REG-049 | Registration | State | App goes to background while loading | Completes task | Registered successfully in background. | Pass
REG-050 | Registration | UX | Success animation/check | Visual feedback | Just a basic toast. Works, but could be better. | Pass
REG-051 | Registration | UX | Email field auto-capitalization | Turned off (first letter shouldn't capitalize) | First letter capitalized by default keyboard. | Fail
REG-052 | Registration | UX | Name field auto-capitalization | Words capitalize automatically | Worked, 'john doe' -> 'John Doe'. | Pass
REG-053 | Registration | Security | Clear App Cache after filling form | Form resets | Wiped correctly. | Pass
REG-054 | Registration | Validation | Double-byte characters (Unicode) in Name | Accepted (e.g., Hindi/Marathi chars) | Stored as '????' in DB. Encoding issue. | Fail
REG-055 | Registration | Validation | Email with IP address (user@[1.1.1.1]) | Rejected | Rejected. | Pass
REG-056 | Registration | Validation | Password exact 8 chars | Accepted (Boundary test) | Accepted. | Pass
REG-057 | Registration | Validation | Password exact 50 chars | Accepted (Boundary test) | Accepted. | Pass
REG-058 | Registration | UI | Password match real-time check | Shows green tick when matched | No real-time feedback, only on submit. | Fail
REG-059 | Registration | UI | Click outside keyboard | Keyboard closes | Closed properly. | Pass
REG-060 | Registration | Logic | Use spaces in Confirm Password | Rejected as mismatch | Rejected correctly. | Pass
REG-061 | Registration | Navigation | Press hardware Back button | Prompts 'Discard changes?' | Exited immediately, lost all typed data. | Fail
REG-062 | Registration | UI | Button ripple effect | Visual click state | Ripple effect visible. | Pass
REG-063 | Registration | State | Receive phone call mid-registration | Form state saved | Resumed correctly. | Pass
REG-064 | Registration | Security | Check backend for rate limiting | Script sends 50 requests | Backend blocked IP after 20 attempts. 429 error. | Pass
REG-065 | Registration | UX | Accessibility/TalkBack on fields | Reads hints properly | Read Name, Email, Pass perfectly. | Pass
REG-066 | Registration | UX | TalkBack on Error states | Reads error messages aloud | Did not read the red error text aloud. | Fail
REG-067 | Registration | Logic | Name with numbers via Copy/Paste | Validation catches it | Caught it on submit. | Pass
REG-068 | Registration | UI | Screen transition animation | Smooth slide/fade | Slid smoothly from Login. | Pass
REG-069 | Registration | Performance | Memory usage on form | Stable under 150MB | Hovered at 90MB. | Pass
REG-071 | Registration | Logic | Email format user@domain.c | Rejected, invalid TLD length | Accepted it. Regex needs updating. | Fail
REG-072 | Registration | Logic | Valid Email domain .edu.in | Accepted | Accepted. | Pass
REG-073 | Registration | UX | Submit with hardware keyboard 'Enter' | Triggers submit | Did nothing. | Fail
REG-074 | Registration | Error Handling | DB offline simulation | Graceful error | Showed 'Server unavailable'. | Pass
REG-075 | Registration | End-to-End | Create account, Login, Verify Dashboard | All working seamlessly | Complete flow successful. | Pass
ATT-001 | Attendance | UI | Navigate to Attendance Module | Subject wise Attendance, Present/Absent Total Statistics | Loaded perfectly. UI is clean. | Pass
ATT-002 | Attendance | UI | Check Default Date | Should default to today's date (faculty) | Defaulted to today's date correctly. | Pass
ATT-003 | Attendance | UI | Check Subject List | Dropdown populates with user's enrolled subjects | Dropdown was empty on first load. Required a refresh. | Fail
ATT-004 | Attendance | Validation | Click 'Present' with no subject selected | Error: 'Please select a subject' | Toast message appeared: 'Select subject first'. | Pass
ATT-005 | Attendance | Functionality | Select Subject -> Click Present | Marks as Present, updates DB | Marked successfully. | Pass
ATT-006 | Attendance | Functionality | Select Subject -> Click Absent | Marks as Absent, updates DB | Marked successfully. | Pass
ATT-007 | Attendance | Validation | Mark Present twice for same subject today | Error: 'Already marked for today' | Button greyed out after first click. Good. | Pass
ATT-008 | Attendance | Logic | Change Absent to Present (Same Day) | Updates record (if allowed by rules) | Threw error: 'Contact admin to change'. Works as intended. | Pass
ATT-009 | Attendance | Boundary | Select tomorrow's date in picker | Future dates disabled or error shown | Picker allowed future date, but API rejected it. UI needs fix. | Fail
ATT-010 | Attendance | Boundary | Select yesterday's date in picker | Allows marking (if past marking is permitted) | Allowed marking for yesterday. | Pass
ATT-011 | Attendance | Logic | Select Saturday/Sunday | Error: 'Weekend marking disabled' | Allowed me to mark attendance on Sunday. Bug. | Fail
ATT-012 | Attendance | Logic | Select known college holiday | Error: 'Holiday, no classes' | Accepted attendance on a public holiday. | Fail
ATT-013 | Attendance | Edge | Spam click 'Present' 10 times | Only 1 DB entry created | Only one entry recorded. Debounce works. | Pass
ATT-014 | Attendance | UI | Button loading state | Spinner during API call | Spinner showed for 1 sec. | Pass
ATT-015 | Attendance | Network | Turn off WiFi -> Click Present | Error: 'No internet connection' | Showed offline warning. | Pass
ATT-016 | Attendance | Network | Offline sync behavior | Marks locally, syncs when online | Did not sync when WiFi turned back on. Data lost. | Fail
ATT-017 | Attendance | Navigation | Go to Dashboard Stats | Stats reflect new attendance immediately | Dashboard updated from 75% to 76%. | Pass
ATT-018 | Attendance | Logic | Verify Total Classes increment | Total classes goes up by 1 | Incremented correctly. | Pass
ATT-019 | Attendance | Logic | Verify Present increment | Present count goes up by 1 | Incremented correctly. | Pass
ATT-020 | Attendance | Logic | Verify Absent increment | Absent count goes up by 1 | Incremented correctly. | Pass
ATT-021 | Attendance | Logic | Percentage calculation (1 Present, 0 Absent) | Shows 100% | Showed 100%. | Pass
ATT-022 | Attendance | Logic | Percentage calculation (1 Present, 1 Absent) | Shows 50% | Showed 50%. | Pass
ATT-023 | Attendance | Logic | Percentage calculation (2 Present, 1 Absent) | Shows 66.67% or 67% | Showed 66.6%. | Pass
ATT-024 | Attendance | UI | Low attendance warning indicator | Turns red if < 75% | Text turned red at 74%. | Pass
ATT-025 | Attendance | Logic | Mark multiple different subjects on same day | Saves independent records | Saved 3 subjects successfully. | Pass
ATT-026 | Attendance | Security | Wait for token expiry -> Mark | Forces logout | Redirected to login. | Pass
ATT-027 | Attendance | Logic | Mark on Leap Year (Feb 29) | Handled correctly | Tested via mock server, worked perfectly. | Pass
ATT-028 | Attendance | Security | Cross-user API attack | Try to send User B's ID in payload | Backend returned 403 Forbidden. Secure. | Pass
ATT-029 | Attendance | State | Select Subject -> Background App -> Return | Subject remains selected | Subject reset to 'Select...'. Annoying UX. | Fail
ATT-030 | Attendance | State | Rotate device on Attendance screen | Layout adjusts, data stays | Layout fine, but subject selection cleared. | Fail
ATT-031 | Attendance | Logic | Time constraint (e.g. 11 PM) | Fails if outside college hours | Allowed marking at 11:30 PM. Might need restriction. | Fail
ATT-033 | Attendance | Navigation | Click 'History' tab | Loads chronological list of records | List loaded instantly. | Pass
ATT-034 | Attendance | Performance | Scroll history with 100+ records | Smooth scrolling, lazy loading | Stuttered heavily after 50 items. Needs RecyclerView optimization. | Fail
ATT-035 | Attendance | UI | Empty History state | Shows 'No records found' image | Showed friendly empty state illustration. | Pass
ATT-036 | Attendance | Logic | Filter History by Subject | Shows only that subject | Filter worked perfectly. | Pass
ATT-037 | Attendance | Logic | Filter History by Month | Shows only that month | Filter applied correctly. | Pass
ATT-038 | Attendance | Logic | Filter yields no results | Shows 'No records for this filter' | Showed correct text. | Pass
ATT-039 | Attendance | Security | SQL Injection in Subject Filter | Sanitized, 400 Bad Request | API rejected payload. | Pass
ATT-040 | Attendance | UI | Dark Mode compatibility | Text readable on dark background | Calendar dates invisible in dark mode (black on black). | Fail
ATT-041 | Attendance | UI | Large Font OS Setting | Doesn't overlap | Mark Present' button text pushed out of bounds. | Fail
ATT-042 | Attendance | Logic | Simultaneous login marking | Device 1 marks Present, Device 2 marks Absent | Device 2 got 'Already marked' error. Good lock. | Pass
ATT-043 | Attendance | Integration | Dashboard widget sync | Updates without manual refresh | Widget updated when returning to home. | Pass
ATT-044 | Attendance | Logic | Marking unenrolled course via API | Returns 400 error | Blocked by backend. | Pass
ATT-045 | Attendance | Boundary | Mark 15 subjects in one day | Validates realistic limits | Allowed 15. Should probably cap at 8-10 max. | Fail
ATT-046 | Attendance | Logic | Admin overrides absent to present | App reflects change | Reflected after pull-to-refresh. | Pass
ATT-047 | Attendance | UI | Pull to refresh on History | Fetches new data | Refreshed correctly. | Pass
ATT-048 | Attendance | Logic | Change device timezone to bypass date lock | Uses server UTC time | Used server time, bypass failed. Secure. | Pass
ATT-049 | Attendance | Network | Submit on 3G throttle | Handles latency gracefully | Spinner spun for 8s, then succeeded. | Pass
ATT-050 | Attendance | Logic | View stats for deleted subject | Handles gracefully | Stats showed 'Unknown Subject' instead of hiding it. | Fail
ATT-051 | Attendance | Security | Rapid concurrent API requests (Burp Suite) | Rate limited | Blocked by 429 Too Many Requests. | Pass
ATT-052 | Attendance | UI | Calendar view - Present days | Green dot under date | Green dot rendered. | fail
ATT-053 | Attendance | UI | Calendar view - Absent days | Red dot under date | Red dot rendered. | fail
ATT-054 | Attendance | UI | Calendar view - Mixed day | Split/Orange dot | Showed split dot correctly. | fail
ATT-055 | Attendance | Logic | Logout User A, Login User B | User B does not see User A's history | Cache cleared completely on logout. | Pass
ATT-056 | Attendance | Security | Tamper with JWT token payload | Rejected by server | Server threw 401 Unauthorized. | Pass
ATT-057 | Attendance | UI | Extremely long subject name | Wraps or truncates cleanly | Wrapped to two lines cleanly. | Pass
ATT-058 | Attendance | Logic | Send boolean instead of date string to API | Type validation catches it | Caught with 400 Bad Request. | Pass
ATT-059 | Attendance | Integration | Notification trigger on Absent | Push notification sent | Received 'You missed a class' notification 5 mins later. | Pass
ATT-060 | Attendance | UI | Pie chart rendering on Stats screen | Renders slices correctly | Chart looks good. | Pass
ATT-061 | Attendance | Logic | Pie chart animation | Animates from 0 to value | Smooth animation on load. | Pass
ATT-062 | Attendance | Boundary | Mark attendance on semester end date | Accepted | Accepted. | Pass
ATT-063 | Attendance | Boundary | Mark attendance 1 day post-semester | Rejected | Threw 'Semester closed' error. | Pass
ATT-065 | Attendance | UX | Double tap on calendar | Does not zoom awkwardly | Viewport locked properly. | Pass
ATT-066 | Attendance | UI | Empty chart state (0 classes) | Shows grey circle, not broken image | Showed grey circle with 'No Data'. | Pass
ATT-067 | Attendance | Network | Drop connection exactly as response arrives | JSON parsing safe | Handled gracefully, didn't crash. | Pass
ATT-068 | Attendance | Logic | Select date from previous year | Blocked | Blocked correctly. | Pass
ATT-069 | Attendance | Logic | Change subject quickly before API returns | Marks for original subject | Marked for the wrong (newly selected) subject. Race condition! | Fail
ATT-070 | Attendance | UX | Accessibility/TalkBack | Reads calendar dates aloud | Read dates perfectly. | Pass
ATT-071 | Attendance | UX | Hardware keyboard traversal | Tab moves through picker/dropdown/buttons | Tab skipped the dropdown entirely. | Fail
ATT-072 | Attendance | Logic | Database timestamp check | Time is logged in UTC | Verified in DB: UTC stored correctly. | Pass
ATT-073 | Attendance | UI | Ripple effect on Mark buttons | Visual feedback | Ripple works. | Pass
ATT-074 | Attendance | Error Handling | Simulate 500 server error | Graceful 'Try again' UI | Showed 'Server unavailable' snackbar. | Pass
ATT-075 | Attendance | End-to-End | Open app -> Select Subject -> Present -> Check Stats | Flow completes under 5 seconds | Completed smoothly in 3.2s. | Pass
QUIZ-001 | Quiz | UI | Navigate to Quiz Module | Displays active quizzes list | List loaded, 2 active quizzes visible. | Pass
QUIZ-002 | Quiz | UI | Click a Quiz card | Opens quiz intro screen | Opened intro with instructions and 'Start' button. | Pass
QUIZ-003 | Quiz | Navigation | Click 'Start Quiz' | Loads Question 1 and starts timer | Q1 loaded, timer started at 15:00. | Pass
QUIZ-004 | Quiz | UI | Check Question UI | Text, Options, Next button visible | All elements perfectly aligned. | Pass
QUIZ-005 | Quiz | Functionality | Select single-choice Option A | Option A highlights (Radio button) | Highlighted correctly in blue. | Pass
QUIZ-006 | Quiz | Functionality | Select Option B after A | A deselects, B selects | Switched correctly. | Pass
QUIZ-007 | Quiz | Functionality | Select multi-choice options A & C | Both highlight (Checkboxes) | Both highlighted with checkmarks. | Pass
QUIZ-008 | Quiz | Navigation | Click 'Next' with answer selected | Moves to Q2 | Transitioned smoothly to Q2. | Pass
QUIZ-009 | Quiz | Navigation | Click 'Next' without answer | Show warning: 'Please select an answer' | Moved to Q2 anyway. No forced answer validation. | Fail
QUIZ-010 | Quiz | Navigation | Click 'Previous' from Q2 | Returns to Q1 | Returned to Q1. | Pass
QUIZ-011 | Quiz | State | Check Q1 state after returning | Previously selected answer is still selected | Answer was wiped clean. User has to re-enter. Critical bug. | Fail
QUIZ-012 | Quiz | UI | Check Timer Countdown | Ticks down every second | Ticks down correctly. | Pass
QUIZ-013 | Quiz | State | Minimize app for 10 seconds during quiz | Timer calculates background time | Timer paused. Exploit to get infinite time! | Fail
QUIZ-014 | Quiz | Functionality | Timer reaches 00:00 | Auto-submits quiz | Quiz auto-submitted exactly at zero. | Pass
QUIZ-015 | Quiz | Functionality | Click 'Submit' button on last question | Prompt 'Are you sure?' | Prompt appeared. | Pass
QUIZ-016 | Quiz | Navigation | Confirm Submit | Calculates score, shows Result screen | Result screen loaded with confetti animation. | Pass
QUIZ-017 | Quiz | Calculation | Score logic: 5 right, 0 wrong | Shows 5/5 or 100% | Showed 100%. | Pass
QUIZ-018 | Quiz | Calculation | Score logic: 2 right, 3 wrong | Shows 2/5 or 40% | Showed 40%. | Pass
QUIZ-019 | Quiz | UI | Review Answers screen | Highlights correct (green) and incorrect (red) | Color coding is correct and intuitive. | Pass
QUIZ-021 | Quiz | Edge | Turn off WiFi mid-quiz | Shows 'Offline mode' or caches | Threw immediate fatal network error. Lost progress. | Fail
QUIZ-022 | Quiz | Edge | Turn WiFi back on before submit | Reconnects and submits | N/A due to previous crash. | Fail
QUIZ-023 | Quiz | Navigation | Press hardware back button during quiz | Warns user progress will be lost | Warning modal appeared. | Pass
QUIZ-024 | Quiz | Navigation | Confirm exit on warning modal | Returns to list, discards attempt | Returned correctly. | Pass
QUIZ-025 | Quiz | Security | Attempt to start same quiz again after completion | Error: 'Already attempted' | Blocked correctly. | Pass
QUIZ-026 | Quiz | Security | Intercept Submit payload via Proxy | Check if correct answers are sent from client | Correct answers are NOT in payload. Computed on backend. Secure. | Pass
QUIZ-027 | Quiz | Security | Modify score payload via Proxy | Try to send {\score\": 100}" | Backend ignored payload score, recalculated natively. Secure. | Pass
QUIZ-028 | Quiz | Performance | Quiz with 50+ questions | Loads without lag | Lagged heavily on question transitions. | Fail
QUIZ-029 | Quiz | Content | Question with very long text | Wraps cleanly, scrollable | Wrapped perfectly, container scrolled. | Pass
QUIZ-030 | Quiz | Content | Question with an Image | Image loads and is zoomable | Image loaded but could not be clicked/zoomed. | Fail
QUIZ-031 | Quiz | Content | Question with Math formulas (LaTeX) | Renders properly | Rendered beautifully. | Pass
QUIZ-032 | Quiz | Content | Question with Code snippet block | Monospace font, formatting kept | Code looked like standard text, lost all indentation. | Fail
QUIZ-033 | Quiz | UI | Progress bar visualization | Updates as user moves through questions | Bar filled up smoothly 10% per question. | Pass
QUIZ-034 | Quiz | Edge | Rapid double-tap 'Next' | Only moves one question | Skipped a question entirely. Debounce needed. | Fail
QUIZ-035 | Quiz | Edge | Rapid double-tap 'Submit' | Only submits once | Submitted twice, recorded two attempts in DB. | Fail
QUIZ-036 | Quiz | Logic | Quiz availability window | Try to access quiz before start time | Button greyed out with countdown. | Pass
QUIZ-037 | Quiz | Logic | Quiz availability window | Try to access quiz after end time | Shows 'Expired'. | Pass
QUIZ-038 | Quiz | State | Screen rotation during quiz | Layout adjusts, timer/answers stay | Timer reset to full 15:00 on rotation! Exploit. | Fail
QUIZ-039 | Quiz | Integration | Score updates Dashboard Leaderboard | Points reflect on home screen | Points updated instantly on dashboard return. | Pass
QUIZ-040 | Quiz | Logic | Clear/Reset answer button | Clears selected radio button | Clear Selection' button works. | Pass
QUIZ-041 | Quiz | UI | Dark mode check | Text readable, images not inverted | Options were white text on white background in dark mode. | Fail
QUIZ-042 | Quiz | UI | Large Font Setting check | Buttons don't overlap | Next' button pushed off screen. | Fail
QUIZ-043 | Quiz | Network | Submit on slow 3G network | Spinner shows, completes eventually | Spun for 12 seconds, completed safely. | Pass
QUIZ-044 | Quiz | Security | Clear app data, login, retry quiz | Still blocked from retaking | Blocked. Status is tied to DB, not local storage. | Pass
QUIZ-047 | Quiz | Logic | Unanswered questions warning on submit | Shows 'You left 3 questions blank' | Warning calculated exact number of blank questions. | Pass
QUIZ-051 | Quiz | Integration | Receive push notification during quiz | Does not interrupt timer/UI | Heads-up notification showed safely. | Pass
QUIZ-053 | Quiz | UI | Timer turns red in last 1 minute | Visual urgency indicator | Turned red at 0:59. | Pass
QUIZ-055 | Quiz | Logic | Submit empty quiz (0 answers) | Score calculates as 0 | Calculated 0% properly. | Pass
QUIZ-058 | Quiz | Navigation | Pull down to refresh during quiz | Disabled | Pull-to-refresh disabled as expected. | Pass
QUIZ-059 | Quiz | UX | Accessibility/TalkBack | Reads question and options aloud | Read nicely. 'Option 1: Paris. Unchecked.' | Pass
QUIZ-060 | Quiz | Logic | Text-input answer (Fill in blank) | Keyboard opens, accepts text | Worked, keyboard shifted UI up properly. | Pass
QUIZ-061 | Quiz | Validation | Text-input case sensitivity | paris' vs 'Paris' | Evaluated correctly (case-insensitive). | Pass
QUIZ-062 | Quiz | Validation | Text-input trailing space | Paris ' | Marked wrong due to trailing space. Needs trim logic. | Fail
QUIZ-063 | Quiz | Security | SQL Injection in text-input answer | Sanitized | Sanitized correctly. | Pass
QUIZ-064 | Quiz | Logic | Maximum attempts (e.g. 3 retries allowed) | Blocks on 4th try | Blocked exactly on 4th attempt. | Pass
QUIZ-065 | Quiz | Navigation | Tap outside modal to dismiss 'Submit?' | Closes modal | Closed modal safely. | Pass
QUIZ-066 | Quiz | Data Flow | Check database for answer blob | Stored as structured JSON | Verified DB, stored cleanly. | Pass
QUIZ-069 | Quiz | Logic | Leaderboard tie-breaker | Sorts by time taken if scores are equal | Ranked correctly based on timestamp. | Pass
QUIZ-075 | Quiz | End-to-End | Complete Quiz from start to Leaderboard | Flawless flow | Completed. Flow is solid aside from the bugs noted above. | Pass
NOT-001 | Notification | UI | Open Notification Tray inside app | Shows empty state if no notifications | Empty state illustration loaded perfectly. | Pass
NOT-003 | Notification | Logic | Trigger notification from backend | Device receives push notification | Arrived in 2 seconds. | Pass
NOT-010 | Notification | Logic | Check in-app tray after receiving push | Notification added to top of list | Added to list correctly. | Pass
NOT-011 | Notification | UI | Check notification UI in tray | Shows Title, Body, Timestamp, Unread dot | All elements visible and aligned. | Pass
NOT-012 | Notification | Logic | Tap unread notification in in-app tray | Unread dot disappears (Mark as read) | Dot disappeared instantly. | Pass
NOT-014 | Notification | Content | Send push with extremely long body text | Text truncates gracefully in OS tray | Truncated with '...' as expected. | Pass
NOT-017 | Notification | Edge | Send push with missing title | Uses default app name as title | Defaulted to 'UniFlow'. Good fallback. | Pass
NOT-018 | Notification | Logic | Receive 5 notifications rapidly | OS groups them into a stack | Grouped as '5 new messages'. | Pass
NOT-020 | Notification | Security | Login as User B, send notification to User A | Device should NOT receive it | Did not receive. Handled correctly. | Pass
NOT-025 | Notification | Data Flow | FCM token generation on first boot | Token sent to backend successfully | Verified in backend logs. Token registered. | Pass
NOT-026 | Notification | Data Flow | FCM token refresh scenario | New token updates on backend | Updated seamlessly without user action. | Pass
NOT-034 | Notification | Data Flow | Database limit on notifications | Keeps only last 100 in app tray | List truncated at 100 correctly. | Pass
NOT-036 | Notification | Logic | Send emojis in push payload | Emojis render correctly | Emojis rendered beautifully. | Pass
NOT-037 | Notification | Performance | Open tray with 100 notifications | Loads smoothly without lag | Slight stutter on first load, then smooth. | Pass
NOT-038 | Notification | UI | Pagination in tray | Scroll down to load older notifications | Lazy loaded older items correctly. | Pass
NOT-039 | Notification | Integration | Attendance low trigger | Auto-sends 'Attendance below 75%' | Received successfully after marking absent. | Pass
NOT-040 | Notification | Integration | Quiz assigned trigger | Auto-sends 'New quiz available' | Received successfully. | Pass
NOT-041 | Notification | Navigation | Dismiss OS notification without clicking | In-app tray still holds the notification | Verified. Item remained in app tray. | Pass
NOT-045 | Notification | Edge | Simulate FCM server outage | App continues to function normally | App worked fine, just no pushes arrived. | Pass
NOT-046 | Notification | UX | Pull to refresh in notification tray | Fetches new items manually | Refreshed correctly. | Pass
NOT-047 | Notification | Security | FCM token hijacking attempt | Verify token binds to device ID | Backend rejected token copy to different device. | Pass
NOT-048 | Notification | UI | Unread count badge inside app navigation | Shows red dot on bell icon | Red dot appeared correctly. | Pass
NOT-049 | Notification | Logic | Clear all notifications | Red dot on bell icon disappears | Dot vanished immediately. | Pass
NOT-055 | Notification | Logic | Rate limiting display | Receive 50 notifications in 1 min | OS bundled them safely, no device freeze. | Pass
NOT-056 | Notification | Edge | Send massive payload (> 4KB) | FCM rejects, app doesn't crash | FCM rejected it, app remained stable. | Pass
NOT-057 | Notification | Data Flow | App cleared from recents | Background service still listens for FCM | Arrived successfully. | Pass
NOT-058 | Notification | Security | Clear app data via Android settings | FCM token invalidated locally | Token wiped, app acts like fresh install. | Pass
NOT-062 | Notification | Content | Payload with special characters (e.g. Arabic) | Renders RTL correctly | Rendered RTL perfectly. | Pass
NOT-067 | Notification | Navigation | Back button from tray | Returns to previous screen | Returned to Home seamlessly. | Pass
NOT-068 | Notification | State | App paused during push fetch | Resumes gracefully | Resumed without crash. | Pass
NOT-075 | Notification | End-to-End | Receive, tap, read, clear, check badge | Complete flow works smoothly | Flow completed without errors. | Pass
INT-001 | Integration | E2E Flow | Register -> Login -> Dashboard | Seamless transition, token retained | Navigated properly, token saved. | Pass
INT-002 | Integration | E2E Flow | Login -> Mark Attendance -> Check Dashboard | Dashboard Attendance widget updates | Widget updated instantly to reflect new stats. | Pass
INT-003 | Integration | E2E Flow | Dashboard -> Take Quiz -> Submit -> Dashboard | Dashboard Leaderboard/Points updates | Points incremented correctly. | Pass
INT-004 | Integration | Navigation | Bottom Navigation routing | Clicking Auth/Att/Quiz tabs switches fragments cleanly | Fragments swapped without reloading full activity. | Pass
INT-006 | Integration | State | Infinite loop prevention | Tap same tab 10 times | Did not add 10 instances to backstack. | Pass
INT-007 | Integration | Security | Token inclusion in headers | Check API calls in Attendance module | JWT token attached to 'Authorization' header properly. | Pass
INT-014 | Integration | UI Consistency | Color palette across modules | Primary blue used consistently | Primary button color matched in all modules. | Pass
INT-015 | Integration | UI Consistency | Typography and Fonts | Same font family used in Auth, Att, and Quiz | Consistent 'Roboto' font throughout. | Pass
INT-018 | Integration | Performance | App cold start time | Time to interactive dashboard | Took 1.8 seconds. Excellent. | Pass
INT-019 | Integration | Performance | App warm start time | Resume from background | Instantaneous resume. | Pass
INT-020 | Integration | Logic | Timezone consistency | Change device timezone -> mark Att -> take Quiz | All payloads used UTC timestamps correctly. | Pass
INT-024 | Integration | UX | Keyboard behavior consistency | Keyboard pushes UI up in all forms | Worked in Auth, but covered fields in Quiz text-input. | Fail
INT-034 | Integration | Logic | Concurrent API requests | Mark attendance AND submit quiz exactly at same time | Both queued and processed safely. | Pass
INT-036 | Integration | Logic | Handle malformed JSON from API | Simulate backend sending broken JSON | Global handler caught parse exception smoothly. | Pass
INT-039 | Integration | Network | Offline mode routing | Launch app with no internet | Loaded cached dashboard, showed offline banner. | Pass
INT-040 | Integration | UI | Empty states consistency | Empty lists show similar graphics | Consistent illustration style across modules. | Pass
INT-050 | Integration | UI | Status bar color | Matches primary app theme | Status bar is solid blue. Matches theme. | Pass
INT-062 | Integration | Data Flow | Logout during API call | Click logout while Attendance is saving | Request cancelled, logged out safely. | Pass
INT-063 | Integration | UX | Double click prevention global | Tap any button twice quickly | Prevented globally via debouncing utility. | Pass
INT-072 | Integration | E2E Flow | Student daily routine flow | Login -> Att -> Check Notifs -> Quiz -> Logout | Smooth 2-minute experience. Core loop is solid. | Pass
INT-073 | Integration | Logic | Data consistency check | Compare client stats with backend DB direct query | Values matched perfectly. | Pass
INT-075 | Integration | E2E Signoff | Vigorous Module Interaction | Final stress test of all systems | Passed with minor UI/UX bugs. Core logic is highly stable. | Pass